Qsoftwares Ltd

Digital Financial Solutions

Next-Gen Digital Banking
& Payments Ecosystem

Technical Proposal  |  Gap Analysis  |  Implementation Plan

Mobile-First Financial Operating System for Emerging Markets

April 2026  |  20-Week Delivery  |  $60,000 Fixed Price

CONFIDENTIAL

# Table of Contents

______________________________

1. Executive Summary

2. Platform Readiness Assessment

3. Gap Analysis — Requirements Matrix

4. Critical Gaps & Solutions

5. BaaS & Sponsor Bank Strategy

6. Recommended Technical Stack

7. Implementation Phases (20 Weeks)

8. Budget Breakdown

9. Third-Party Dependencies

10. Risk Assessment

11. Our Competitive Advantage

12. Edge Case Matrix

13. Deliverables & Next Steps

# 1. Executive Summary

______________________________

We propose building a comprehensive digital banking and payments ecosystem for an emerging market, leveraging our existing Apache Fineract core banking infrastructure, 9 payment provider integrations, and proven mobile banking patterns. Our platform already covers ~60% of the required backend infrastructure, dramatically reducing build time from 12+ months to 20 weeks.

Key Decision: We recommend Flutter for the cross-platform mobile app (iOS + Android from a single codebase), with Riverpod state management and Drift for offline-first local storage.

The platform serves as a high-utility retail banking app for individuals and a robust payment-acceptance suite for merchants, replacing cash-heavy legacy systems with a secure, mobile-first Financial Operating System.

| Metric | Value |
| --- | --- |
| Backend Infrastructure Ready | ~60% |
| Payment Providers Integrated | 9 (Africa + Asia + Global) |
| Delivery Timeline | 20 weeks (5 months) |
| Fixed Budget | $60,000 |

# 2. Platform Readiness Assessment

______________________________

Our existing platform comprises three production applications with a shared Apache Fineract backend. These capabilities transfer directly to the NeoBank project:

| Capability | Details | Status |
| --- | --- | --- |
| Core Banking Engine | Fineract — double-entry GL, loans, savings, multi-currency | Production |
| Payment Integrations | M-Pesa, Airtel, MTN, Flutterwave, Paystack, Cellulant, AT, Razorpay, Stripe | Production |
| React Admin Dashboard | Client CRUD, loan/savings management, mobile money, reports | Production |
| Tax Compliance | eTIMS/KRA integration — invoices, credit notes, tax codes | Production |
| Credit Scoring | PataScore — bank statement + M-Pesa analysis | Production |
| Client Management | KYC document storage, client lifecycle, group/center hierarchy | Production |
| Mobile UX Patterns | 50+ screens: auth, dashboard, loans, payments, QR, biometric | Proven |
| Multi-Tenant Architecture | Isolate data per organization from day one | Production |

# 3. Gap Analysis — Requirements Matrix

______________________________

## A. Digital Banking Infrastructure

| Requirement | Current State | Gap Level |
| --- | --- | --- |
| Tiered Accounts (Personal + Business) | Fineract supports client types + savings products | LOW |
| Automated KYC/AML (ID + liveness) | Document storage only, no automated verification | HIGH |
| Shadow Ledgering (real-time) | Full GL exists; pending transaction layer needed | MEDIUM |
| Multi-currency reconciliation | Multi-currency supported; FX feeds needed | LOW |

## B. Card Management System

| Requirement | Current State | Gap Level |
| --- | --- | --- |
| Physical prepaid debit cards | No card infrastructure | CRITICAL |
| Virtual instant cards | None | CRITICAL |
| Freeze/unfreeze, spend limits, alerts | None | CRITICAL |
| Contactless (NFC) + Chip & PIN | None — requires card issuing partner | CRITICAL |

## C. Merchant & POS Solutions

| Requirement | Current State | Gap Level |
| --- | --- | --- |
| Bluetooth POS terminals | No POS infrastructure | HIGH |
| SoftPOS / Tap-to-Phone | None | HIGH |
| Instant settlement | Mobile money B2C disbursement exists | MEDIUM |

## D. P2P Ecosystem

| Requirement | Current State | Gap Level |
| --- | --- | --- |
| Instant P2P via phone/alias/QR | QR screen + basic transfers exist | MEDIUM |
| QR for P2P + Merchant payments | Basic QR in mobile app | MEDIUM |

## E. Technical & Security Standards

| Requirement | Current State | Gap Level |
| --- | --- | --- |
| SOC2/PCI-DSS compliance | No compliance framework | CRITICAL |
| OAuth2 + JWT authentication | Basic auth only | HIGH |
| Data residency compliance | Not architected for regional deployment | HIGH |
| Mobile security (cert pinning) | Biometric exists; cert pinning missing | MEDIUM |
| High-concurrency backend | Fineract Spring Boot + modular arch | LOW |

# 4. Critical Gaps & Solutions

______________________________

## 4.1 Card Issuing & Management

This is the most significant gap. Card infrastructure requires a BaaS partner already PCI-DSS certified and connected to card networks.

| Region | Card Issuing Partners |
| --- | --- |
| Africa | Union54, Flutterwave (virtual cards), Paystack Issuing |
| Asia | Stripe Issuing, Rapyd, Nium |
| Global | Marqeta, Stripe Issuing, Adyen Issuing |

Architecture: Flutter App → Our Backend → Card Issuing API → Webhook receiver → Fineract GL posting. Our systems never touch raw card numbers (tokenization). Effort: 4–5 weeks.

## 4.2 KYC/AML Automated Workflows

Automated identity verification is mandatory. We integrate with Smile Identity (Africa) or Onfido (Global) for ID verification, liveness detection, OCR, and AML/sanctions screening.

KYC Flow: Capture ID (front+back) → Liveness check → OCR extraction → AML screening → Risk score → Auto-approve or manual queue → Fineract account activation. Effort: 2–3 weeks.

## 4.3 PCI-DSS & SOC2 Compliance

By using a BaaS partner for card issuing, we reduce PCI-DSS scope to SAQ-A. SOC2 requires encryption at rest, access logging, vulnerability scanning, and documented security policies. Effort: 3–4 weeks.

## 4.4 Merchant & POS Solutions

Hardware POS: PAX A920 / Sunmi V2 Pro — Bluetooth + 4G terminals

SoftPOS: Mastercard Tap on Phone SDK or Visa Tap to Phone

Settlement: Extend existing M-Pesa/Airtel B2C for instant payouts

QR Standard: EMVCo QR specification for interoperable payments

Effort: 4–5 weeks

# 5. BaaS & Sponsor Bank Strategy

______________________________

The product requires a licensed sponsor bank that holds deposits, provides banking rails, issues cards, and ensures regulatory compliance.

| Region | BaaS Partner | Capabilities | Card Issuing |
| --- | --- | --- | --- |
| East Africa | Cellulant, Stanbic API | Deposits, payments | Via Visa/MC partner |
| West Africa | Flutterwave, Paystack | Deposits, cards | Flutterwave virtual |
| Southern Africa | Stitch, Investec API | Open banking | Investec issuing |
| South Asia | Razorpay X, Setu | Neo-banking, UPI | Partner bank cards |
| Southeast Asia | Brankas, Rapyd | Wallets | Rapyd issuing |
| Global | Marqeta, Stripe Treasury | Full stack | Marqeta/Stripe cards |

# 6. Recommended Technical Stack

______________________________

## Backend (Extend Existing)

| Component | Technology | Rationale |
| --- | --- | --- |
| Core Banking | Apache Fineract (Java 21) | Already built, proven |
| API Gateway | Kong / AWS API Gateway | Rate limiting, auth, routing |
| Auth Server | Keycloak | OAuth2 + JWT + MFA |
| Cache | Redis | Shadow ledger, sessions |
| Message Queue | Apache Kafka | Event sourcing, webhooks |
| Database | PostgreSQL + Redis | Fineract-compatible |
| File Storage | AWS S3 | KYC docs, statements |
| Monitoring | Grafana + Prometheus | Full observability |

## Flutter Mobile App

| Component | Package | Purpose |
| --- | --- | --- |
| Framework | Flutter 3.x (Dart) | Cross-platform |
| State Mgmt | Riverpod 2.x | Compile-safe, testable |
| HTTP Client | Dio + Retrofit | Type-safe API calls |
| Local DB | Drift (SQLite) | Offline-first |
| Secure Storage | flutter_secure_storage | Keychain/Keystore |
| Biometrics | local_auth | Fingerprint + Face |
| NFC | nfc_manager | Tap-to-pay |
| Camera/OCR | camera + google_mlkit | KYC capture |
| QR | qr_flutter + mobile_scanner | Generate + scan |

# 7. Implementation Phases (20 Weeks)

______________________________

## Phase 1: Foundation & Security (Weeks 1–4)

| Timeline | Deliverable | Details |
| --- | --- | --- |
| Week 1 | OAuth2 + JWT auth server | Replace basic auth with Keycloak |
| Week 1–2 | Infrastructure hardening | TLS 1.3, WAF, encryption, VPC |
| Week 2–3 | KYC/AML integration | Smile ID — ID verification + liveness |
| Week 3–4 | BaaS partner vetting | Evaluate 3–5 partners |
| Week 4 | Security documentation | SOC2 evidence, PCI-DSS SAQ |

## Phase 2: Core Banking Enhancement (Weeks 5–8)

| Timeline | Deliverable | Details |
| --- | --- | --- |
| Week 5 | Tiered accounts | Basic/Standard/Premium tiers |
| Week 5–6 | Shadow ledger (Redis) | Real-time pending balance |
| Week 6–7 | P2P payment engine | Phone lookup, alias, QR |
| Week 7–8 | Multi-currency | FX rates, conversion |
| Week 8 | Notification engine | FCM + WebSocket alerts |

## Phase 3: Card Issuing (Weeks 9–12)

| Timeline | Deliverable | Details |
| --- | --- | --- |
| Week 9–10 | Card issuing API | Virtual + physical cards |
| Week 10–11 | Card management UI | Freeze, limits, PIN |
| Week 11–12 | Card transactions | Auth webhooks, GL posting |
| Week 12 | Card security | Dynamic CVV, 3DS, tokenization |

## Phase 4: Flutter App (Weeks 9–16) — Parallel

| Timeline | Deliverable | Details |
| --- | --- | --- |
| Week 9–10 | App shell + auth | Flutter, Riverpod, KYC flow |
| Week 11–12 | Banking screens | Dashboard, accounts, P2P |
| Week 13–14 | Card screens | Card UI, NFC |
| Week 14–15 | Payment screens | 9 providers, QR |
| Week 15–16 | Security + polish | Cert pinning, testing |

## Phase 5: Merchant & POS (Weeks 13–16)

| Timeline | Deliverable | Details |
| --- | --- | --- |
| Week 13 | Merchant onboarding | KYC, verification, setup |
| Week 13–14 | POS integration | PAX/Sunmi SDK |
| Week 14–15 | SoftPOS | NFC payment acceptance |
| Week 15–16 | Settlement engine | Instant/T+1, MDR fees |

## Phase 6: QA & Launch (Weeks 17–20)

| Timeline | Deliverable | Details |
| --- | --- | --- |
| Week 17–18 | Automated testing | Unit + E2E tests |
| Week 18–19 | Penetration testing | Third-party audit |
| Week 19–20 | Compliance docs | SOC2, PCI-DSS, edge cases |
| Week 20 | Soft launch | Beta release |

# 8. Budget Breakdown

______________________________

| Phase | Duration | Key Deliverables | Cost |
| --- | --- | --- | --- |
| Phase 1: Foundation & Security | 4 weeks | OAuth2, KYC, infra, BaaS vetting | $12,000 |
| Phase 2: Core Banking | 4 weeks | Tiered accounts, shadow ledger, P2P, FX | $12,000 |
| Phase 3: Card Issuing | 4 weeks | Card API, management UI, transactions | $12,000 |
| Phase 4: Flutter App | 8 weeks | Cross-platform app, 50+ screens | $12,000 |
| Phase 5: Merchant & POS | 4 weeks | POS, SoftPOS, settlement | $8,000 |
| Phase 6: QA & Launch | 4 weeks | Testing, pen test, compliance | $4,000 |
| TOTAL | 20 weeks | Complete Digital Banking Platform | $60,000 |

Note: Phases 3 and 4 run in parallel, so total calendar time is 20 weeks (5 months).

# 9. Third-Party Dependencies

______________________________

Ongoing operational costs (not included in $60K build cost):

| Service | Provider | Est. Monthly Cost | Notes |
| --- | --- | --- | --- |
| KYC/AML | Smile ID / Onfido | $200–500/mo | $0.10–0.50 per check |
| Card Issuing | Marqeta / Stripe | Variable | Per-card + per-txn |
| Cloud | AWS / GCP | $500–2,000/mo | Scale-dependent |
| POS Terminals | PAX / Sunmi | $100–300/unit | One-time |
| SMS | Africa's Talking | $50–200/mo | Per-message |
| Sponsor Bank | Regional | Negotiated | Revenue share |

# 10. Risk Assessment

______________________________

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| BaaS partner delays | HIGH | HIGH | Start Week 1, 2 backup options |
| PCI-DSS timeline | MEDIUM | HIGH | Use BaaS PCI scope |
| Sponsor bank approval | HIGH | CRITICAL | Begin immediately |
| Card network cert | MEDIUM | MEDIUM | Pre-certified BaaS |
| Flutter low-end perf | LOW | MEDIUM | Profile from Week 10 |
| Data residency | MEDIUM | HIGH | Multi-region K8s |

# 11. Our Competitive Advantage

______________________________

What We Bring (Saves 3–4 Months vs. Starting from Scratch):

| Asset | Value |
| --- | --- |
| Apache Fineract Core Banking | Double-entry GL, loans, savings, multi-currency, multi-tenant |
| 9 Payment Providers | M-Pesa, Airtel, MTN, Flutterwave, Paystack, Cellulant, AT, Razorpay, Stripe |
| React Admin Dashboard | Full CRUD: clients, loans, savings, reports, mobile money, tax compliance |
| Mobile Banking UX | 50+ proven screens translating directly to Flutter |
| Credit Scoring | PataScore — bank statement + M-Pesa analysis |

Matching Your Brief Section 4 — Technical Delivery Capabilities:

| Your Requirement | Our Evidence |
| --- | --- |
| BaaS Strategy & Discovery | 9 payment providers across Africa + Asia |
| Financial Backend Engineering | Fineract ledger + 9 payment webhooks + GL posting |
| Secure Mobile Development | Biometric auth, payment flows, KYC capture |
| Infrastructure Hardening | Cloud deployment, multi-tenant, API security |
| Fintech Project Orchestration | Multi-app ecosystem (web + 2 mobile) |
| Financial QA | Ledger reconciliation, transaction testing |

# 12. Edge Case Matrix

______________________________

Representative sample of our Edge Case Matrix for transaction failure states:

| Scenario | Expected Behavior | Recovery |
| --- | --- | --- |
| Card auth timeout | Hold funds, retry once, release 30min | Auto-reversal + notify |
| Double STK push | Idempotency key prevents duplicate | Return existing txn ID |
| KYC verification fails | Account in 'Pending' state | Manual review queue |
| Offline P2P transfer | Queue locally, sync online | Conflict detection |
| POS battery dies mid-txn | Transaction not completed | 'Incomplete' receipt |
| FX rate changes mid-transfer | Lock rate 60s at initiation | Re-quote on expiry |
| Sponsor bank downtime | Degrade to mobile money | Auto-switch rail |
| Card fraud detected | Instant freeze + push | Unfreeze or replace |

# 13. Deliverables & Next Steps

______________________________

## Final Deliverables

Flutter Mobile App (iOS + Android) — Full digital banking experience

React Admin Dashboard (enhanced) — Staff operations, merchant management

Backend API Layer (extended) — OAuth2, card issuing, KYC, shadow ledger, P2P

Infrastructure — PCI-compliant cloud, multi-region, CI/CD pipeline

Documentation — API docs, architecture diagrams, SOC2, edge case matrix

Testing — Unit, integration, pen test, stress test reports

## Recommended Next Steps

| # | Step | Details |
| --- | --- | --- |
| 1 | NDA Signing | Before disclosing brand name and specifications |
| 2 | BaaS Discovery Call | 1-week sprint to evaluate 3–5 BaaS partners |
| 3 | Technical Deep-Dive | 2-hour session with your CTO |
| 4 | Contract & Kickoff | Phase 1 begins immediately after agreement |

Ready to Build the Future of Payments?

Qsoftwares Ltd
info@qsoftwares.org  |  +254 710 401 008
www.qsoftwares.org