## Slide 1
Qsoftwares Ltd
Next-Gen Digital Banking
& Payments Ecosystem
Technical Proposal | Gap Analysis | Plan
April 2026 | 20-Week Delivery
Platform Readiness
60%
Backend Ready
9
Payment Providers
20
Weeks to Launch
$60K
Fixed Budget
Mobile-First Financial Operating System
for Emerging Markets
CONFIDENTIAL

## Slide 2
Executive Summary
Why We're the Right Partner
Qsoftwares Ltd | info@qsoftwares.org | +254 710 401 008
CONFIDENTIAL
We propose building a comprehensive digital banking ecosystem leveraging our existing Apache Fineract core banking, 9 payment providers, and proven mobile patterns. ~60% of backend infrastructure is already built.
• Flutter cross-platform app (iOS + Android) with bank-grade security
• Card issuing via BaaS partner (Marqeta/Stripe) — virtual + physical
• Automated KYC/AML via Smile ID (20+ African countries)
• POS & SoftPOS for merchant payment acceptance
• P2P payments via phone, alias, and QR codes
• SOC2/PCI-DSS compliance through architecture + BaaS scope
Key Decision: Flutter + Riverpod + Drift for offline-first, cross-platform mobile.

## Slide 3
Platform Readiness
What We Already Have (Saves 3–4 Months)
Qsoftwares Ltd | info@qsoftwares.org | +254 710 401 008
CONFIDENTIAL
Core Banking
Apache Fineract Double-entry GL Loans & Savings Multi-currency
9 Payment Providers
M-Pesa, Airtel, MTN Flutterwave, Paystack Cellulant, AT Razorpay, Stripe
React Dashboard
Client CRUD Loan/Savings Mgmt Mobile Money Ops eTIMS Tax System
Mobile UX Patterns
50+ Proven Screens Auth, Payments, QR Biometric Auth Loan Applications
Additional: Credit Scoring (PataScore), Multi-Tenant Architecture, eTIMS Tax Compliance
Architecture: Flutter App → API Gateway → Fineract Backend → BaaS + Card Issuer + KYC

## Slide 4
Gap Analysis
Requirements vs. Current Capabilities
Qsoftwares Ltd | info@qsoftwares.org | +254 710 401 008
CONFIDENTIAL
Area | Requirement | Current State | Gap
Banking | Tiered Accounts | Fineract supports client types | LOW
Banking | KYC/AML Automation | Document storage only | HIGH
Banking | Shadow Ledger | GL exists; pending layer needed | MEDIUM
Cards | Virtual + Physical Cards | No card infrastructure | CRITICAL
Cards | Freeze/Limits/NFC | None | CRITICAL
Merchant | POS Terminals + SoftPOS | No POS infrastructure | HIGH
P2P | Phone/Alias/QR Payments | Basic QR + transfers exist | MEDIUM
Security | SOC2/PCI-DSS | No compliance framework | CRITICAL
Security | OAuth2 + JWT | Basic auth only | HIGH

## Slide 5
Critical Gap Solutions
How We Bridge the Gaps
Qsoftwares Ltd | info@qsoftwares.org | +254 710 401 008
CONFIDENTIAL
Card Issuing
BaaS Partner Integration Marqeta / Stripe Issuing Virtual + Physical cards Tokenization (no raw card data) NFC + Chip & PIN via network Effort: 4–5 weeks
KYC/AML
Identity Verification Smile ID (Africa) / Onfido ID capture + liveness check OCR + AML screening Auto-approve or manual queue Effort: 2–3 weeks
PCI/SOC2
Compliance Framework SAQ-A (outsourced card data) TLS 1.3 enforcement Encryption at rest (KMS) Automated vuln scanning Effort: 3–4 weeks
Merchant/POS
Payment Acceptance PAX/Sunmi hardware POS Mastercard Tap on Phone EMVCo QR standard Instant settlement engine Effort: 4–5 weeks

## Slide 6
BaaS & Sponsor Bank Strategy
Regional Partners for Banking Rails & Card Issuing
Qsoftwares Ltd | info@qsoftwares.org | +254 710 401 008
CONFIDENTIAL
Region | BaaS Partner | Capabilities | Card Issuing
East Africa | Cellulant, Stanbic API | Deposits, payments | Via Visa/MC partner
West Africa | Flutterwave, Paystack | Deposits, cards | Flutterwave virtual
Southern Africa | Stitch, Investec API | Open banking | Investec issuing
South Asia | Razorpay X, Setu | Neo-banking, UPI | Partner bank cards
Southeast Asia | Brankas, Rapyd | Wallets | Rapyd issuing
Global | Marqeta, Stripe Treasury | Full stack | Marqeta/Stripe cards
Architecture Layers: Layer 1: Flutter App + React Dashboard → Layer 2: Kong API Gateway → Layer 3: Fineract Backend → Layer 4: BaaS + Card Issuer + KYC Provider

## Slide 7
Technical Stack
Proven Technologies for Bank-Grade Systems
Qsoftwares Ltd | info@qsoftwares.org | +254 710 401 008
CONFIDENTIAL
Backend (Extend Existing)
Component | Technology
Core Banking | Apache Fineract (Java 21)
API Gateway | Kong / AWS API Gateway
Auth Server | Keycloak (OAuth2 + JWT)
Cache | Redis
Queue | Apache Kafka
Database | PostgreSQL
Monitoring | Grafana + Prometheus
Flutter Mobile App
Component | Package
Framework | Flutter 3.x (Dart)
State Mgmt | Riverpod 2.x
HTTP | Dio + Retrofit
Local DB | Drift (SQLite)
Biometrics | local_auth
NFC | nfc_manager
QR Codes | qr_flutter + scanner

## Slide 8
Implementation Timeline
6 Phases Over 20 Weeks
Qsoftwares Ltd | info@qsoftwares.org | +254 710 401 008
CONFIDENTIAL
Phase 1
Foundation & Security
Weeks 1–4
$12K
→
Phase 2
Core Banking Enhancement
Weeks 5–8
$12K
→
Phase 3
Card Issuing & Management
Weeks 9–12
$12K
→
Phase 4
Flutter Mobile App
Weeks 9–16
$12K
→
Phase 5
Merchant & POS
Weeks 13–16
$8K
→
Phase 6
QA & Launch
Weeks 17–20
$4K
Note: Phases 3 & 4 run in parallel (separate teams). Total calendar time: 20 weeks.
P1: OAuth2, KYC, infra hardening | P2: Tiered accounts, shadow ledger, P2P | P3: Card API, management UI | P4: Full Flutter app (50+ screens) | P5: POS, SoftPOS, settlement | P6: Pen test, SOC2, beta launch

## Slide 9
Budget Breakdown
$60,000 Fixed Price — 20-Week Delivery
Qsoftwares Ltd | info@qsoftwares.org | +254 710 401 008
CONFIDENTIAL
Phase | Duration | Key Deliverables | Cost
Phase 1: Foundation & Security | 4 weeks | OAuth2, KYC/AML, infra, BaaS vetting | $12,000
Phase 2: Core Banking Enhancement | 4 weeks | Tiered accounts, shadow ledger, P2P, FX | $12,000
Phase 3: Card Issuing & Management | 4 weeks | Card API, management UI, transactions | $12,000
Phase 4: Flutter Mobile App | 8 weeks | Cross-platform app, 50+ screens | $12,000
Phase 5: Merchant & POS | 4 weeks | POS, SoftPOS, settlement engine | $8,000
Phase 6: QA, Compliance & Launch | 4 weeks | Testing, pen test, SOC2, beta | $4,000
TOTAL | 20 weeks | Complete Digital Banking Platform | $60,000
Third-party costs (client responsibility): KYC ($200–500/mo), Card Issuing (per-txn), Cloud ($500–2K/mo), POS hardware ($100–300/unit), SMS ($50–200/mo), Sponsor Bank (negotiated)

## Slide 10
Why Qsoftwares
Matching Your Brief — Section 4 Capabilities
Qsoftwares Ltd | info@qsoftwares.org | +254 710 401 008
CONFIDENTIAL
Your Requirement | Our Evidence
BaaS Strategy & Discovery | Experience with 9 payment providers across Africa + Asia
Financial Backend Engineering | Apache Fineract ledger + 9 payment webhooks + GL posting
Secure Mobile Development | Biometric auth, payment flows, KYC document capture
Infrastructure Hardening | Cloud deployment, multi-tenant, API security
Fintech Project Orchestration | Multi-app ecosystem (web + 2 mobile) with shared backend
Financial QA | Ledger reconciliation, transaction testing, compliance documentation
Edge Case Matrix maintained for all transaction failure states: card auth timeout, double STK push, offline P2P, POS battery failure, FX rate changes, sponsor bank downtime, card fraud.

## Slide 11
Ready to Build the
Future of Payments?
1. NDA Signing — Before disclosing brand name and full specifications
2. BaaS Discovery Call — 1-week sprint to evaluate 3–5 BaaS partners
3. Technical Deep-Dive — 2-hour session with your CTO
4. Contract & Kickoff — Phase 1 begins immediately
Qsoftwares Ltd
info@qsoftwares.org | +254 710 401 008 | www.qsoftwares.org
$60,000 Fixed Price | 20-Week Delivery | Flutter + Fineract + BaaS
CONFIDENTIAL